## WSJF Table
Status Summary
|  | Status | Count
|  | New | 3
|  | In Progress | 3
|  | Done | 3
|  | Blocked | 1
Date | Number | Feature / Project | User-Business Value | Time Criticality | Risk Reduction / Opportunity | Job Size | WSJF Score | % Complete | Status
2025-04-13 | 1 | Cloud Migration | 13 | 7 | 6 | 13 | 2 | 30 | In Progress
2025-04-14 | 2 | Mobile Dashboard | 6 | 4 | 5 | 5 | 3 | 40 | In Progress
2025-04-15 | 3 | Reporting API | 6 | 5 | 4 | 4 | 3.75 | 0 | New
2025-04-16 | 4 | Chatbot Integration | 8 | 6 | 7 | 5 | 4.2 | 100 | Done
2025-04-17 | 5 | Security Audit | 9 | 8 | 9 | 5 | 5.2 | 100 | Done
2025-04-18 | 6 | Improve Search | 8 | 6 | 4 | 4 | 4.5 | 0 | New
2025-04-19 | 8 | Billing Upgrade | 5 | 3 | 2 | 2 | 5 | 0 | New
2025-04-20 | 7 | User Profile Revamp | 7 | 5 | 3 | 3 | 5 | 60 | In Progress
2025-04-21 | 9 | SSO Enablement | 7 | 6 | 5 | 3 | 6 | 100 | Done
2025-04-22 | 11 | Dashboard Dark Mode | 6 | 4 | 3 | 2 | 6.5 | 0 | Blocked